SAICM/ICCM.5/Bureau.2/INF/10

	[image: image1.png]



	SAICM/ICCM.5/Bureau.2/INF/10

	[image: image2.png]P e Strategic Approach

SAlCIM tonternational
v

Chemicals Management





	Distr.: General

22 November 2016

English only


Second meeting of the Bureau of the 

International Conference on Chemicals Management for its fifth session 

Sao Paulo, Brazil
7-8 December 2016

Item 6 (c) of the provisional agenda*

Implementation towards the achievement of the 2020 goal: 
Update on the third SAICM progress report (2014-2016)

Joint SAICM Secretariat and WHO Draft Workplan for SAICM 2014-2016 Progress Reporting

Note by the secretariat
1.  The secretariat has the honour to circulate in the annex to the present note a joint draft workplan, prepared by the SAICM secretariat and the World Health Organization (WHO), setting out an indicative timeframe for undertaking the progress reporting activities for 2014 – 2016. The information is available for information of the Bureau.
3.  Background information on periodic SAICM reporting is available at the following link:

www.saicm.org/index.php?option=com_content&view=article&id=115&Itemid=512
ANNEX

Indicative timeframe – Joint SAICM secretariat and WHO draft workplan 

SAICM 2014-2016 Progress Reporting

	Progress Report



	Activity


	Timeframe
	Responsibility

	1. Review reporting tool and provide recommendations for revision.


	November 2016 – January 2017
	WHO / SAICM Secretariat



	2. Revise electronic reporting tool.
	February – March 

2017


	WHO 

	3. Call for reporting to SAICM stakeholders, including the word version of the reporting tool (indicating that the tool will open in April 2017).


	March 2017
	SAICM Secretariat



	4. Reporting window open for stakeholder input.
(Launch in April 2017) 


	April – July  2017
	WHO data management.

SAICM Secretariat liaison with stakeholders.

	5. Data collation.


	August – September 2017
	WHO

	6. Data analysis / report development.


	September 2017 – January 2018 
	SAICM Secretariat.

Liaison with WHO to access reporting tool.



	7. Final progress report development.
	February – April 2018
	SAICM Secretariat



	8. Translation. 
	May – June 2018


	SAICM Secretariat



	9. Posting for OEWG3.
	July 2018
	SAICM Secretariat




________________
*SAICM/ICCM.5/Bureau.2/1





